## Sheet1
| Cycle 0 Debrief | Cycle 1 Debrief | Cycle 2 Debrief | Cycle 3 Debrief | Cycle 4 Debrief | Cycle 5 Debrief
Did we achieve our objective? | In terms of achieving our objective of completing our submissions for Cycle 0, we succeeded. However, we did not succeed in properly clarifying the advantage of our product compared to competing, existing EMRs. Consequently, we produced good drafts for our cycle 0 design foundation document, but not with a full understanding of our project to tackle. We plan to address this deficiency by scheduling a follow up meeting with our sponsors this week to further clarify some of our project's problem and specs/design criteria. | We successfully turned in all of our assignments on time. However, we did not succeed in interviewing all the people that we wanted to get feedback from for our product background (REMS, medical technician, Epic employee, sponsors, second gastroenterologist, second cardiologist). | It is hard to say at this moment since we have not yet reached the Cycle 2 deadline. If we went off of the previously discussed "internal deadliine" of one week, then no we did not reach our objective since we have not completed our new deliverables nor finished our Cycle 2 objective execution. | We did not complete all of our objectives (fully integrated platform)-- we got 95% of the way there. This is in part because we did not properly priotize objectives, uploading patient chart data was pushed off meaning we did not have sufficient time to complete downloading patient data on the specialty physician pages. It was also a matter of misinterpreting what work each objective would entail and delegating through the whole objective completion timeline. For example, when we tried to complete this objective, we said that we'd need to make the MT pages and the cardiology pages functional. So we delegated *styling* of the pages, but not the database integration aspect. The database integration was also dependent on medical technician page work, so it was hard to spread this work out over time as opposed to figuring it out as we went through in the last few weeks of objective work. | We achieved most of our objectives in time for the senior design showcase. For the specialty physician interface, it was difficult to combine code that other teammates were working on because of Git issues. There could have been better communication on the progress of the pages so it could be integrated earlier on. | Yes, we have achieved all of our new objectives outlined in cycle 5. Notably, we have officially deployed our website on www.virtual-physical.com, while having implemented comprehensive, end-to-end funtionalities that truly facilitate the traditional physical pipeline and rendered access to medical exams more readily available. Throughout the semester, we have realized our mission of making specialty care more accessible.
What did we do right? | 1. We were open about what tasks we were comfortable completing, and worked well to delegate tasks to individuals. 2. The roles and responsibilities were carried out and understood by the team members. 3. Initially, workload distribution was a bit unbalanced (which stemmed from a lack of understanding of the instructions for cycle 0 deliverables early on); however, we quickly realized it and re-delegated tasks in a more fair way. 4. Task assistance was requested for certain aspects of an assignment and team members were able to work together to finish the tasks. In the future, we could understand the scope of the assignments in the beginning and better delegate the workload. 5. The team's leadership was balanced and worked out for the assignments that we were delegated. All disagreements within the team were resolved through explanation of logic. | 1. We clarified our specs! 2. We completed our first engineering sketch (flowcharts) to help us brainstorm and make a clear path forward for cycle 2 and 3 objectives. 3. We were more proactive about delegating our workload. 4. We utilized class time to complete assignments as a team, giving us a chance to ask each other questions that would otherwise make the assignments difficult to complete individually. | 1. We realized that our early morning meetings could be held on zoom sometimes 2. We front-loaded more of our work for cycle 2 3. We ordered our medical devices early on in cycle 2 and received most of them before thanksgiving (digital stethoscope came week following thanksgiving) 4. We communicated with our sponsors more and recieved helpful feedback in how to approach certain features and integration and where to prioritize our efforts in the protyping process such as including the phonocardiogram images instead of extracting the audio data from the Eko app generated PDF 5. We utilized class and outside time to work on prototyping and recieve feedback from another team member when our Cycle 2 objectives shared similarities and built off each other | 1. We created team agendas for each weekly meeting, met every week, and filled out the weekly updates on our own time. This made routine weekly meetings more effective (and shorter), and kept the team motivated and on top of the team's progress. 2. We also scheduled team working sessions either in person or zoom for objective work, these were not necessairly the whole team, but were very effective in completing objective work. 3. We created and kept closer track of Gantt Chart to track deliverable/competition deadlines and spread out this work evenly. 4. We left more time to obtain feedback so that we would increase our likelihood of hearing back on time. 5. Team members were willing to help others to complete tasks, especially for integrating the UIs with the database and how to upload data | 1. We implemented a lot of the feedback from poster and pitch practice sessions that helped during the final design showcase 2. Team members were willing to help others to complete tasks, especially for the guidance system & summary aspects 3. We were able to work on a lot of the Cycle 4 objectives on our own and schedule meetings with other team members if we needed help, improving overall efficiency | 1. We incorporated feedback from our previous cycles into our final design. 2. We are able to revise and iterate on our previous designs. 3. We are able to go one step further and make our platform compliant with the current standard of care and medical regulations.
What did we do wrong? | 1. We did not finish rough drafts early enough to get feedback from all mentors. 2. We underutilized Santiago as a resource for us: our meetings were not very well-planned on our part. We plan to include agenda notes for not only our faculty sponsor meeting, but also for our design mentor. 3. We did not keep an updated record of our progress (accomplished/not accomplished) on our weekly update documents. 4. We could improve upon communication by utilizing the google calendar and putting zoom links for the corresponding meeting. | 1. We did not finish rough drafts with sufficient time to get feedback. 2. We struggled with keeping mentors and sponsors in the loop with major decision changes in regards to the scope of our project. 3. We did not clarify confusion about deliverables early on (mostly for functional decomposition), meaning that we were forced to rush completion near the due date. 4. Some team members volunteered to take on a lot of assignments, leading to some imbalance in workload. Maybe team members that know that they can take on more work can volunteer themselves more often. | 1. We stopped meeting weekly near the end of the semester 2. We did not finish our deliverables a week before the deadline 3. Did not delegate deliverables early enough to complete our deliverables a week before the deadline | 1. We did not properly prioritize objective work, so the objectives that were dependent on other other objectives to be completed did not have sufficient time to be completed. 2. The workload balance was very uneven. Vincent had a much lighter workload/code that he worked on had to be redone. 3. Did not complete all deliverables a week before the deadline. | 1. We did not start on the deliverables early enough, a week before the deadline, as some assignments relied on portions of other ones 2. There was sometimes a lack of communication and loss track of progress as teammates would forget to fill in their weekly updates or finish their sections right before meeting or deadline | 1. In the end, we did not get to have med professionals to test our platform and instead found a couple of Rice students to use our web platform and give us feecback. 2. In terms of making the presentation slides, we should have probably started earlier and planned ahead more thoroughly.
What should we do next time? Is it different from what you had planned in the previous cycle? | 1. We plan to finish our documents earlier (a week before the deadline) so we can not only iterate through more drafts, but also obtain feedback from all our mentors. To be more mindful of task delegation and individual workload, we will properly educate ourselves on the deliverable instructions early on. 2. We will now make agendas for both mentor meetings (faculty and design) in our weekly update. 3. Update task progress in subsequent weekly update to keep track of what progress other individuals have completed. | 1. We plan to finalize our documents a week before the deadline in order to give ample time for mentor and professor feedback and keep them in the loop about changes with the project design. (not different from last cycle) 2. Assign one team member to take care of emailing (for when we want to schedule interviews or have questions for our sponsors, for example). (new from last cycle) | 1. Finalize deliverables a week before the deadline to receive feedback (same as last cycle) 2. Continue routine communication with sponsors (new) 3. Figure out how to utilize meetings for specific objectives we want to achieve (meeting on zoom, outside of class or with individual teammates for specific tasks) | 1. Split up work more evenly. 2. The goals from the previous cycle still apply here. 3. Get feedback from people working in the industry such as UX designers and human factors grad students on how to improve the UI and user experience 4. Find more medical technicians with low experience/training and get their feedback on the learning curve and UI | 1. Find more medical technicians with low experience/training and get their feedback on the learning curve and UI 2. Start on deliverables in advance, espcially letting teammates know if you need another section done to finish yours | 1. Find more medical professionals as users and have more backup plans in case we did not receive replies in time. 2. Manage time and deadlines more effectively. 3. Try to expand our care to other specialty medicine branches as well.
Did you follow-through with what you had planned from the previous cycle? Was it helpful? | N/A | No we did not follow through for completing all of our documents a week before the deadline to have enough time for design mentor feedback. However, we did inform ourselves on the deliverable instructions early enough this time. We have made agendas for all of our mentor meetings. We did not start doing #3; we didn't really find a need for it since we started meeting during class time and updated each other in person. | We followed through with assigning one team member to take care of emailing. Michelle emails our weekly updates. | We communicated much more with our sponsors this cycle. We met every single week for weekly team meetings. We delegated the deliverables much in advance of the deadline. We edited our team contract so that now Melissa takes care of assembling team weekly meeting agendas and has the team on track as the project manager. | We split up the work slightly more evenly this cycle as some members were able to focus on deliverables or specific cyle 4 objectives. | We did, as we were able to stay on top of our work delegated, and we did learn from our previous work and feedback given from the faculty.
Other helpful discussion questions to consider:
- Was communication clear? How can we improve it?
- Were roles and responsibilities understood?
- Was workload distribution equitable?
- Was task assistance requested or offered?
- How was the leadership?
- What additional resources can we bring in to help us for next time?